## Sheet1
ID | Task | Storied (Check) | Start Date | Due Date | Estimated Duration | Resources (Devs) | Technology | Description
1 | CAT Scheduler
1.1 | Documents
1.1.1 | Requirements Specifications
1.1.2 | Design Specifications
1.1.3 | Work Breakdown Structure
1.1.4 | Project Schedule
1.1.5 | Risk Assessment
1.1.6 | Midterm Presentation
1.1.7 | Final Presentation
1.1.8 | Sponsor Delivery
1.2 | Database
1.2.1 | Schema
1.2.1.1 | Design
1.2.1.1.1 | Determine what information is necessary to store in the database
1.2.1.1.2 | Decide on naming conventions
1.2.1.1.3 | Determine tables with primary and foreign keys
1.2.1.1.4 | Build entity relationship diagram
1.2.1.1.5 | Normalize the tables and refine the schema
1.2.1.1.6 | Update entity relationship diagram
1.2.1.2 | Implementation
1.2.2 | Scripts
1.2.2.1 | Design Scripts
1.2.2.1.1 | Determine functionality needed for minimum viable product
1.2.2.1.2 | Implement scripts
1.2.2.1.2.1 | Term
1.2.2.1.2.1.1 | List Terms | US105, US106
1.2.2.1.2.1.2 | Add Term | US107, US108, US109
1.2.2.1.2.1.3 | Edit Term | US112, US113, US110
1.2.2.1.2.1.4 | Delete Term | US111, US114
1.2.2.1.2.2 | Student
1.2.2.1.2.2.1 | List Students Term | US116, US117
1.2.2.1.2.2.2 | Add Student | US118, US119, US115
1.2.2.1.2.2.3 | Edit Student | US120, US121
1.2.2.1.2.2.4 | Delete Student | US122
1.2.2.1.2.3 | Availability
1.2.2.1.2.3.1 | List Availability | US123
1.2.2.1.2.3.2 | Update Availability | US124
1.2.2.1.2.3.3 | Remove Availability | US125
1.3 | Administrative Interface
1.3.1 | Database Interface
1.3.1.1 | Administrator Schedule Submit
1.3.1.2 | Student Schedule Query
1.3.1.2.1 | Create Scripts
1.3.1.2.1.1 | Get Student Day/Times
1.3.1.2.1.2 | Get Student Information
1.3.1.3 | Administrative Schedule Change
1.3.1.3.1 | Create Scripts
1.3.1.3.1.1 | Create Term
1.3.1.3.1.2 | Retrieve Term
1.3.2 | Visual Design
1.3.2.1 | Create Design Draft
1.3.2.1.1 | Determine Administrative Pages
1.3.2.1.2 | Determine Administrative Tools
1.3.2.2 | Build Design
1.3.2.2.1 | Implement Pages
1.3.2.2.1.1 | Create Term | US100
1.3.2.2.1.2 | View Term | US101
1.3.2.2.1.3 | Display List of Students | US103
1.3.2.2.2 | Connect to Design Interface
1.4 | Client Interface
1.4.1 | Database Interface
1.4.1.1 | Update Availability | US102
1.4.1.2 | View Availability by Term
1.4.1.3 | Retrieve Term
1.4.2 | Visual Design
1.4.2.1 | Select Term | US104
1.4.2.2 | Week View for Submission
1.4.2.3 | Shift Preference
1.4.2.4 | Notifications
1.4.2.5 | Submit Changes
1.5 | Testing
1.5.1 | Administrative Interface
1.5.1.1 | Test Administrative View
1.5.1.1.1 | Ensure agreement between admin and client information
1.5.1.1.2 | Verify buttons are linked to correct features