## Risks
Risk Management Matrix
Project |  |  | CAT Scheduler | [5 empty] | Project #
Project manager |  |  | Castle | [5 empty] | Sponsor | Computer Action Team
Updated
ID | Risk Description | Probability | Severity | Risk | Category | Trigger Event/Indicator | Risk Response and Description | Contingency Plan | Owner | Status | Date Entered | Date to Review
1 | Sponsor disappears | 2 | 4 | 8 |  | accidents, discontinueing the product | Contact the backup Sponsor and Bart | Ask for backup Sponsors | Team Lead
2 | Team Member disappears | 2 | 2 | 4 | personal | Family emergency, accident and natural causes | distribute the work between other team members | Assign at least two members for each task | All members
3 | Natural causes | 1 | 3 | 3 |  | Earth quake, War, bombing etc. | The show must go on |  | All members
4 | Loss of data/Backup | 2 | 4 | 8 | Technology | Human error, servers crashing | Start over and work extra hours | github, CAT stash, local back up | All members
5 | Miss comunication with sponsor | 4 | 4 | 16 | Technology and personal | Miss communication between sponcer and the team member for the requirements | get in contact with the sponsor and review the information again | have multiple members present at the meeting with sponsors, check review the meeting notes with sponsor after each meeting | All members
6 |  |  |  | 0
7 |  |  |  | 0
8 |  |  |  | 0
9 |  |  |  | 0
10 |  |  |  | 0
11 |  |  |  | 0
12 |  |  |  | 0
13 |  |  |  | 0
14 |  |  |  | 0
15 |  |  |  | 0